## POEC
POEC Project Tracker
Project No. | Project Title | Project Description | Project Year | Project Status | Focus Area | Recommendation No. | Recommendation | Recommendation Status | Notes | Last Updated
24-01 | Accommodations for Campus Guests | Creation of an accessible and equitable experience for accommodation request protocols for campus guests. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 1: | Further research into the need for, and feasibility of, a new position description for an individual responsible for event-based and third-party disability accommodations. This position description may also include other duties related to compliance. Identify and consult with any CSU campuses with similar positions. | Complete | A position description has been written and classified for this work. With the campus hiring freeze, the position remains on hold but is ready for recruitment when funding permits. | 2025-08-15
24-01 | Accommodations for Campus Guests | Creation of an accessible and equitable experience for accommodation request protocols for campus guests. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 2: | Convene a committee of campus accessibility partners to review the campus’ current timelines, processes, and procedures that relate to the physical CSUCI campus, and make recommendations for improvements. | Complete | Please visit the University Accessibility Committee webpage. | 2025-08-15
24-01 | Accommodations for Campus Guests | Creation of an accessible and equitable experience for accommodation request protocols for campus guests. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 3: | Research the cost associated with purchasing items that may be utilized to provide common disability accommodations for event guests such as wheelchairs, ramps, and specialized wheelchair-accessible golf carts. | In Progress | A comprehensive budget quote has been requested from University Events related to the items referenced (quantity, brand, etc.). A determination will then be made regarding what items may be purchased pending available funding. | 2025-08-15
24-01 | Accommodations for Campus Guests | Creation of an accessible and equitable experience for accommodation request protocols for campus guests. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 4: | Consult with the Chancellor’s Office and other relevant governmental compliance officers to identify the best practices as they relate to training for employees concerning ADA compliance and universal design. | Ongoing | Consultation has been ongoing and trainings have been planned for the 2024-25AY and 2025-26 AY. | 2025-08-15
24-01 | Accommodations for Campus Guests | Creation of an accessible and equitable experience for accommodation request protocols for campus guests. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 5: | Review current event planning process to include consultation about and reconsideration of campus guest accommodations and universal accessibility. | In Progress | A full review of the campus guest accommodations and universal accessibility process is underway, which includes the incorporation of additional efficiencies. | 2025-08-15
24-02 | Forms & Workflow | An evaluation was conducted to identify opportunities to simplify form submissions and student requests through increased automation in routing and communication, with the goal of improving operational efficiency and enhancing the student experience. The project focused on streamlining student-initiated requests by exploring automation solutions to improve routing, communication, and overall operational efficiency in the Registrar’s Office. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 1: | Utilize custom web applications with PeopleSoft integration to create automated routing. | Ongoing | Expanded the custom web application to include full term withdrawal in additional to the course withdrawal and Extended University now also uses the withdrawal request application, creating a similar student experience for both state support and self support students. Determined that Adobe Sign was the best solution for the most used form, which is the "Petition for Exception." This petition form is a catch-all form and approvers vary by request. The Adobe Sign petition for exception workflow has been implemented and there has been an improvement in turnaround time. | 2025-08-15
24-02 | Forms & Workflow | An evaluation was conducted to identify opportunities to simplify form submissions and student requests through increased automation in routing and communication, with the goal of improving operational efficiency and enhancing the student experience. The project focused on streamlining student-initiated requests by exploring automation solutions to improve routing, communication, and overall operational efficiency in the Registrar’s Office. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 2: | Ensure workflow documentation is memorialized should the need arise to migrate to a different platform in the future. | Complete | All workflows have been documented and prioritized. | 2025-08-15
24-02 | Forms & Workflow | An evaluation was conducted to identify opportunities to simplify form submissions and student requests through increased automation in routing and communication, with the goal of improving operational efficiency and enhancing the student experience. The project focused on streamlining student-initiated requests by exploring automation solutions to improve routing, communication, and overall operational efficiency in the Registrar’s Office. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 3: | Prepare to overhaul student forms thoughtfully and sustainably by organizing all request types, documenting the various approvers, and determining the most frequently submitted forms to assist in building out a realistic timeline. | Complete | All workflows have been documented and prioritized. | 2025-08-15
24-02 | Forms & Workflow | An evaluation was conducted to identify opportunities to simplify form submissions and student requests through increased automation in routing and communication, with the goal of improving operational efficiency and enhancing the student experience. The project focused on streamlining student-initiated requests by exploring automation solutions to improve routing, communication, and overall operational efficiency in the Registrar’s Office. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 4: | Work with the Registrar’s Office to examine the resources and direction available on our website to streamline the information to students. Processes identified as confusing or difficult to explain should be targeted first. | Complete | Information streamlined to incorporate new forms and workflows. | 2025-08-15
24-02 | Forms & Workflow | An evaluation was conducted to identify opportunities to simplify form submissions and student requests through increased automation in routing and communication, with the goal of improving operational efficiency and enhancing the student experience. The project focused on streamlining student-initiated requests by exploring automation solutions to improve routing, communication, and overall operational efficiency in the Registrar’s Office. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 5: | Collaborate with Academic Advising to get feedback from students to ensure the information is easily digestible. | Ongoing |  | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 1: | Ask for university-wide direction from leadership including a shared vision, five-year goals, detailed enrollment plan, campus-wide support, incentives, and recognition. | Complete | A Strategic Enrollment Management Plan was finalized with Chancellor's Office support in spring 2025. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 2: | Establish formal committees and structures for central outreach and recruitment, data collaboration, cross-training, peer mentorship, and overall strategy. | Ongoing | Structures have been established including cross-divisional units to ensure alignment in strategy. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 3: | Develop comprehensive resources and platforms including a data dashboard, centralized repository of recruitment materials, and online platform for event/program sharing. | Ongoing | Full implementation of Slate as primary enrollment platform to track data related to recruitment in summer 2025. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 4: | Implement data-driven decision making through standardized metrics, collaborative analysis, and integration with strategic planning. | Ongoing | Key Performance Indicators (KPIs) have been established within the enrollment process to track the effectiveness of various recruitment efforts. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 5: | Increase communication and collaboration through regular meetings, workshops, shared calendars, and a culture of data sharing. | Ongoing | Standing meetings have been established with campus leadership, Enrollment Management leadership, and Institutional Research. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 6: | Offer targeted support and incentives for disconnected units and collaborative initiatives. | Ongoing | Enrollment Management has developed tabling materials and recruitment packets to present a unified campus presence and message. These resources are available to all campus units. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 7: | Develop and implement a unified messaging framework to explain the CSUCI vision and story to prospective students and their families. | Ongoing | In partnership with Communication & Public Relations and the ISAT #3 Subcommittee on Strategic Marketing, value statements for tiered audiences and brand messaging are being developed for use by Enrollment Management recruitment staff, faculty ambassadors, and other campus representatives engaged in University outreach. | 2025-08-15
24-03 | Recruitment Coordination | The project examined CSUCI’s outreach and recruitment efforts across Ventura County, identifying opportunities to enhance collaboration and resource sharing among academic and non-academic units to strengthen the pipeline for future enrollment. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Recruitment & Enrollment | Recommendation 8: | Establish a plan for sustainable practices over ad-hoc practices to determine what unit(s) will house the work identified in the above areas and be responsible for data collection and overall coordination. | Ongoing | With the assistance of Best Practice Solutions (BPS), working to establish sustainable practices that will scale across campus. | 2025-08-15
24-04 | Student Gift Cards | The project examined critical challenges in administrative processes and the role of administrative staff in managing student research gift cards. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 1: | Invite Procurement to engage in a consultation to expand and elaborate on any future plans, such as the implementation of initiatives like “Tango Card.” Evaluate whether this proposed process eliminates liability applicable to Administrative Support. | Complete | The Tango platform has been implemented, visit the Gift Card Guidelines and Procedures for additional information. | 2025-08-15
24-04 | Student Gift Cards | The project examined critical challenges in administrative processes and the role of administrative staff in managing student research gift cards. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 2: | Extend invitations to Financial Aid for specialized consultations, specifically about 1) reporting gift cards as financial aid and 2) about the authority of Financial Aid to use professional judgment to increase students’ COA if they participate in research. Assess whether this process minimizes the impact on student’s financial aid award and what flexibility, if any, exists within the overall process. | Complete | (1) Financial Aid has been an ongoing partner at the table when working to fully understand any implications related to the use of gift cards, including how cost of attendance may be impacted and any appropriate options available to the students. (2) Professional judgement is guided by Federal regulations, and it allows the Financial Aid & Scholarships office to review a student's individual circumstances to determine if there is a reason to adjust a student's cost of attendance. This requires a student to demonstrate an increase in their educational expenses in alignment with the criteria outlined within the regulations. | 2025-08-15
24-04 | Student Gift Cards | The project examined critical challenges in administrative processes and the role of administrative staff in managing student research gift cards. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 3: | Offer administrative staff the opportunity to collaborate in the process, ensuring their voices are heard in reviewing and refining procedures. Evaluate the effectiveness of these collaborative spaces in improving knowledge and professional development. | Ongoing | While not yet fully implemented, staff representation on committees and working groups has increased. Advocacy continues to ensure diverse perspectives are considered before process or policy changes are implemented. This will remain an ongoing effort, particularly as leadership over various elements and processes evolves. | 2025-08-15
24-04 | Student Gift Cards | The project examined critical challenges in administrative processes and the role of administrative staff in managing student research gift cards. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 4: | Advocate for development of universal “POEC form” that integrates the framework and the 4-Frame Analysis Cheat Sheet (PDF, 179 KB). This form should be accessible to all members of the campus community. | n/a | Feedback received; however, not tied to specific project. | 2025-08-15
24-04 | Student Gift Cards | The project examined critical challenges in administrative processes and the role of administrative staff in managing student research gift cards. | 2023-24 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 5: | Incorporate a dedicated section on the campus website with operational processes that can be reviewed and further developed for clarity and transparency. Step-by-step workflow library available to all staff. Prevent guarding of information by promoting transparency and inclusivity in decision-making processes. Cultivate a culture of openness and trust, enabling circulation of knowledge among all stakeholders. | In Progress | With the launch of the new website in 2025-26 AY, an Intraweb for employees will be available. The intraweb will allow for increased sharing of information among employees, rather than needing to include process information on the public-facing webpages. | 2025-08-15
24-05 | Schedule of Classes | The project reviewed CSUCI’s Schedule of Classes (SoC) data workflow, which spans five separate platforms without a unified support structure or coordinated strategy. The team analyzed the platforms, responsible units, and related processes to identify inefficiencies and recommend improvements to enhance both the user experience and staff operations. | 2023-24 AY | Not yet started. | Campus Services | Recommendation 1: | Streamline & Support: SoC platforms should be streamlined such that only 1-2 are maintained per campus role or use, with an overarching strategy implemented to ensure full campus awareness and buy-in; data collection on use and efficacy should be incorporated in current institutional research initiatives and individual units should be empowered to manage the platforms they are responsible for more directly. | Not yet started. |  | 2025-08-15
24-05 | Schedule of Classes | The project reviewed CSUCI’s Schedule of Classes (SoC) data workflow, which spans five separate platforms without a unified support structure or coordinated strategy. The team analyzed the platforms, responsible units, and related processes to identify inefficiencies and recommend improvements to enhance both the user experience and staff operations. | 2023-24 AY | Not yet started. | Campus Services | Recommendation 2: | Research & Data Collection: Implement methods to monitor SoC platform use data within Enrollment Management; incorporate technology use and digital user experience metrics into existing ITS and/or OIR data collection efforts; publish data to broader campus community to enable better use of current platforms; provide support for small-scale student feedback initiatives on digital user experience within individual units to inform department/unit-level or division-level decisions; increase opportunities for staff to engage in professional and academic research. | Not yet started. |  | 2025-08-15
24-05 | Schedule of Classes | The project reviewed CSUCI’s Schedule of Classes (SoC) data workflow, which spans five separate platforms without a unified support structure or coordinated strategy. The team analyzed the platforms, responsible units, and related processes to identify inefficiencies and recommend improvements to enhance both the user experience and staff operations. | 2023-24 AY | Not yet started. | Campus Services | Recommendation 3: | Formalize the authority of the University Registrar and Registrar’s Office staff over the student records and SoC data housed in CI Records, registration process, and all SoC and registration platforms; support expansion of Student Systems and/or Registrar’s Office staff to include a dedicated programmer to allow for consolidation of platform oversight under the Enrollment Management umbrella. | Not yet started. |  | 2025-08-15
24-05 | Schedule of Classes | The project reviewed CSUCI’s Schedule of Classes (SoC) data workflow, which spans five separate platforms without a unified support structure or coordinated strategy. The team analyzed the platforms, responsible units, and related processes to identify inefficiencies and recommend improvements to enhance both the user experience and staff operations. | 2023-24 AY | Not yet started. | Campus Services | Recommendation 4: | Unified Strategy & Goals: Pair platforms to user groups to maximize efficacy; implement a strategic marketing campaign to increase awareness and use of identified primary platform(s) by role or purpose. | Not yet started. |  | 2025-08-15
25-01 | Committee Productivity Evaluation | A substantial amount of administrator, staff, and faculty time is spent in long-standing committee meetings with unclear results, straining resources and schedules. This project evaluated the relevance, effectiveness, and membership of these committees to ensure alignment with current priorities and the production of meaningful outcomes. | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 1: | Conduct a systematic review of existing committees to assess their mission alignment, deliverables, and impact over the past 6–12 months. This process should determine whether each committee should continue, be suspended, or sunset entirely, using a structured decision tree to guide evaluations. | Ongoing | Assessment tools have been created and area available on the Organizational Effectiveness webpage. This review is necessary at the campus- and division-level on an annual basis. | 2025-08-15
25-01 | Committee Productivity Evaluation | A substantial amount of administrator, staff, and faculty time is spent in long-standing committee meetings with unclear results, straining resources and schedules. This project evaluated the relevance, effectiveness, and membership of these committees to ensure alignment with current priorities and the production of meaningful outcomes. | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 2: | Before forming new committees, it is essential to analyze the return on investment by establishing a clear rationale, defined scope, and set timeline in advance. Deliverables, authority, and sunset dates should be clearly outlined, and committee formation should not be the default approach to solving problems. | Ongoing | Assessment tools have been created to assist in the decision around whether or not a new committee should be formed. This review is needed on an ongoing basis. | 2025-08-15
25-01 | Committee Productivity Evaluation | A substantial amount of administrator, staff, and faculty time is spent in long-standing committee meetings with unclear results, straining resources and schedules. This project evaluated the relevance, effectiveness, and membership of these committees to ensure alignment with current priorities and the production of meaningful outcomes. | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 3: | Committee operations can be strengthened through targeted training in project management, facilitation, note-taking, record keeping, and role clarity. All members should understand their role in the teaming cycle, with accountability reinforced through transparent documentation and regular progress tracking. | Ongoing | A campus Committee Guidebook has been created which outlines the standards, expectations, and responsibilities of each committee member that serves on a committee. Annual reporting will be required, minimally. | 2025-08-15
25-01 | Committee Productivity Evaluation | A substantial amount of administrator, staff, and faculty time is spent in long-standing committee meetings with unclear results, straining resources and schedules. This project evaluated the relevance, effectiveness, and membership of these committees to ensure alignment with current priorities and the production of meaningful outcomes. | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Operations | Recommendation 4: | Finally, institutional knowledge should be leveraged by centralizing committee documentation and outcomes at the division level within a shared system. Creating a comprehensive knowledge base would facilitate cross-divisional learning, support continuity, and preserve valuable insights over time. | Ongoing | A shared digital folder for all campus-level committees to retain committee materials and records has been created out of the Office of the President. This will house all presidential-appointed committee records. Divisions have been asked to create similar structures for division-level committees. | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 1: | The project team recommends continuing the POEC initiative with a focus on gathering additional data to inform decision-making. This includes administering surveys and conducting interviews with peer institutions, as well as reintroducing internal surveys to library users. These efforts will help establish a clearer picture of organizational practices, service needs, and opportunities for improvement. | Ongoing |  | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 2: | Long-term improvement planning and prioritization should also be a priority. The library should commit to sustained internal improvement efforts, starting with the ideas identified in this report. This will require restoring faculty positions as the budget allows to ensure adequate operational capacity, increasing the collections budget annually to offset rising subscription costs and support new academic programs, and securing ongoing funding for essential services such as the digital equipment program. | Ongoing |  | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 3: | To strengthen outreach and academic integration, the team recommends envisioning and implementing a librarian liaison model. With support from the Interim Dean, the library should explore variations of this model to determine what best fits current staffing and campus needs. This approach would deepen collaboration with faculty, improve communication, and provide clear points of contact for students across disciplines. | Ongoing |  | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 4: | Partnerships will be critical to advancing these goals. The library should work closely with Institutional Research to develop meaningful, anonymized metrics that link library use to student learning, success, and retention. | Ongoing |  | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Complete - remaining and ongoing work transitioned to operational leadership. | Campus Services | Recommendation 5: | Collaboration with University Advancement should be expanded to secure funding for space improvements, digital resources, and special initiatives, as well as to ensure librarian representation in long-term campus planning. | Ongoing |  | 2025-08-15
25-02 | Library Subject Liaison Models |  | 2024-25 AY | Not yet started. | Campus Services | Recommendation 6: | Addressing organizational structure deficits is essential. The campus should commit to maintaining a stable Strategic Apex by hiring a Dean of the Library with both leadership and librarianship experience, as well as re-establishing a Middle Line management structure to improve coordination, communication, and operational efficiency. This will provide the foundation needed to sustain improvements and adapt to evolving campus needs. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 1: | Establish a centralized communication platform, such as an Adobe workflow, that incorporates each area of authority and tracks completed tasks. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 2: | Create a standardized, campus-wide procedural framework with universal guidance to ensure consistency, reduce disruptions from turnover, and clearly distinguish onboarding activities from orientation. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 3: | Streamline timelines across all areas to increase efficiency, reduce variability, and produce predictable outcomes. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 4: | Normalize early onboarding requirements, provide applicants with clear timelines, and offer robust resources for complex content to reduce barriers to entry. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 5: | Assign clear ownership for each stage of the process to maintain accountability. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 6: | Provide consistent and frequent training for all participants in the process, including MPPs and approvers. | Not yet started. |  | 2025-08-15
25-03 | Onboarding |  | 2024-25 AY | Not yet started. | Campus Operations | Recommendation 7: | Expand approval authority to include a secondary approver in each office or department to minimize bottlenecks and maintain workflow continuity. | Not yet started. |  | 2025-08-15